## TASK TRACKER
Professional Development Materials Tracker
Project Resources
Project Staff
| Developer | Task | Status | Editor | Status | Deadline | Start Date | End Date
Session 1 | Amanda | Learner Guide | Ready for review | Michael | Changes needed | 2025-12-01 | 2025-11-01 | 2025-11-28
| John | Participant Handout | Completed | Rachel | Approved | 2025-12-05 | 2025-11-02 | 2025-11-20
Session 2 | Michael | Slide Deck | In Progress | Amanda | Pending | 2025-01-10 | 2024-12-01
Session 3 | Rachel | Workbook Draft | Not Started | John |  | 2025-02-15
Session 4 | Amanda | Trainer Script | In Progress | Michael | Review scheduled | 2025-03-05 | 2025-01-15
Session 5 | John | Assessment Quiz | Ready for review | Rachel | Under review | 2026-03-25 | 2026-01-20
| Michael | Infographic | Completed | Amanda | Approved | 2026-04-01 | 2026-01-05 | 2026-01-20

## ABOUT (hidden)
FIELD | DETAILS
AUTHOR | RUTUJA SANTOSH SHANKPALE
PROJECT TITLE | GUIDED PROJECT: CREATE A PROJECT MANAGEMENT TRACKER USING MICROSOFT EXCEL
COURSE/SOURCE | COURSERA
INSTRUCTOR | PAULA DEL REY
CREATED ON | 2025-12-01
CONTACT | www.linkedin.com/in/rutujashankpale
COPYRIGHT | © 2025 RUTUJA SHANKPALE. ORIGINAL WORK. ALL RIGHTS RESERVED.